## Project Summary
Project Summary (read-only)
Project Name | Ocean Smart Roadmap V1.0
Project Manager | noppasit.jo@ocean.co.th
Start date | 2020-08-03
Finish date | 2021-01-01
Days | Pro
Progress | 9.061%
Work hours | Pro
Remaining work hours | Pro
Remaining work days | Pro
Remaining weeks | Pro
Cost

## Task Schedule
[6 empty] | Aug 2020 |  |  |  | Sep 2020 |  |  |  | Oct 2020 |  |  |  |  | Nov 2020 |  |  |  | Dec 2020 |  |  |  |  | Jan 2021 |  |  |  | Feb 2021 |  |  |  | Mar 2021 |  |  |  | Apr 2021 |  |  |  |  | May 2021 |  |  |  | Jun 2021 |  |  |  | Jul 2021 |  |  |  |  | Aug 2021 |  |  |  | Sep 2021 |  |  |  |  | Oct 2021 |  |  |  | Nov 2021 |  |  |  | Dec 2021
WBS | Task description | Start date | Finish date | Progress | Remark | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
wbs | task | start | finish | progress |  | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | #
¦
1 | Phase 0 | 2020-08-03 | 2020-09-30 | 16.18% |  | = | ¦
1.1 | Develop - Phase 0.1 | 2020-08-03 | 2020-08-14 | 50% |  | = | ¦
1.1.1 | ยกเลิกขายแบบประกัน FNA/Mini-FNA/Ocean Smart | 2020-08-03 | 2020-08-14 | 100% |  | = | =
1.1.1.1 | Ord E58 โอเชี่ยนไลฟ์ เซฟรับทรัพย์ 15/8 | 2020-08-03 | 2020-08-14 | 100% |  | = | =
1.1.1.2 | Ord A37 โอเชี่ยนไลฟ์ คุ้มค่าตลอดชีพ 90/20 | 2020-08-03 | 2020-08-14 | 100% |  | = | =
1.1.1.3 | Ord 130 ไทยสมุทร เซฟดั่งใจ 12/6 | 2020-08-03 | 2020-08-14 | 100% |  | = | =
1.1.1.4 | Ord 494 ไทยสมุทรสบายสบาย 30/5 | 2020-08-03 | 2020-08-14 | 100% |  | = | =
1.1.1.5 | Ord 495 ไทยสมุทรสบายสบาย 30/10 | 2020-08-03 | 2020-08-14 | 100% |  | = | =
1.1.1.6 | Ord 221 สบายชัวร์ (ไม่กลัวอะไรเลย) | 2020-08-03 | 2020-08-14 | 100% |  | = | =
1.1.1.7 | Ind 145 ไทยสมุทรคุ้มนาน 90/20 | 2020-08-03 | 2020-08-14 | 100% |  | = | =
1.1.2 | New Product 7 แบบประกัน (Ocean Smart) | 2020-08-03 | 2020-08-14 | 0% |  |  | ¦
1.1.2.1 | O188 (ปรับค่าคอม,ทุนต่ำ) | 2020-08-03 | 2020-08-14 | 0% |  |  | ¦
1.1.2.2 | O193 (ปรับค่าคอม,ทุนต่ำ) | 2020-08-03 | 2020-08-14 | 0% |  |  | ¦
1.1.2.3 | O539 เพื่อนคู่ชีวิต B450 (20/15) (ปรับค่าคอม) | 2020-08-03 | 2020-08-14 | 0% |  |  | ¦
1.1.2.4 | O218 สบายชัวร์ (ปรับค่าคอม) | 2020-08-03 | 2020-08-14 | 0% |  |  | ¦
1.1.2.5 | O496 ไทยสมุทรสบายสบาย 30/15 (ปรับค่าคอม) | 2020-08-03 | 2020-08-14 | 0% |  |  | ¦
1.1.2.6 | I154 คุ้มทวี (20/15) (ปรับค่าคอม) | 2020-08-03 | 2020-08-14 | 0% |  |  | ¦
1.1.2.7 | I156 คุ้มทวี 20/10 (ปรับค่าคอม) | 2020-08-03 | 2020-08-14 | 0% |  |  | ¦
1.2 | SIT - Phase 0.1 (FNA/Mini-FNA, New Product) include 40 products | 2020-08-17 | 2020-09-04 | 0% |  |  | ¦
1.2.1 | การยกเลิกขายแบบประกัน FNA/Mini-FNA/Ocean Smart | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.2 | New Product 7 แบบประกัน (Ocean Smart) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.2.1 | O188 (ปรับค่าคอม,ทุนต่ำ) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.2.2 | O193 (ปรับค่าคอม,ทุนต่ำ) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.2.3 | O539 เพื่อนคู่ชีวิต B450 (20/15) (ปรับค่าคอม) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.2.4 | O218 สบายชัวร์ (ปรับค่าคอม) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.2.5 | O496 ไทยสมุทรสบายสบาย 30/15 (ปรับค่าคอม) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.2.6 | I154 คุ้มทวี (20/15) (ปรับค่าคอม) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.2.7 | I156 คุ้มทวี 20/10 (ปรับค่าคอม) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.2.3 | Retest | 2020-08-17 | 2020-09-04 | 0% |  |  | ¦
1.2.3.1 | ทดสอบแบบประกันเก่า 40 รายการ | 2020-08-17 | 2020-09-04 | 0% |  |  | ¦
1.3 | Develop - Phase 0.2 | 2020-08-17 | 2020-09-04 | 0% |  |  | ¦
1.3.1 | New Product 3 แบบประกัน (Ocean Smart) (Cont.) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.1.1 | E73 สมาร์ท โกล 15/7 | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.1.2 | E74 สมาร์ท โกล 25/5 | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.1.3 | E75 สมาร์ท โพรเทคชัน 99/99 (Agent) | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.2 | ปรับ UX/UI, Flow การ Login, Lib | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.2.1 | ปรับ Layout และการแสดงผล | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.2.2 | ปรับ Flow การ Login - Traditional | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.2.3 | รองรับ MSA Production | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.2.4 | Flag สำหรับ Version e-App | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.3 | Checklist deploy on Production | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.3.1 | จัดทำ Checklist | 2020-08-17 | 2020-08-28 | 0% |  |  | ¦
1.3.4 | Health Checkup-AMLO (Recheck AMLO หรือ MIB) | 2020-08-31 | 2020-09-04 | 0% |  |  | ¦
1.3.4.1 | Service ตรวจสภาวะ (geras) | 2020-08-31 | 2020-09-04 | 0% |  |  | ¦
1.3.4.2 | Service ตรวจสภาวะ (msa-salesiilus) | 2020-08-31 | 2020-09-04 | 0% |  |  | ¦
1.3.4.3 | UI ผลการตรวสถาวะ - ตัวแทน | 2020-08-31 | 2020-09-04 | 0% |  |  | ¦
1.3.4.4 | UI ผลการตรวสถาวะ - ไม่ใช่ตัวแทน | 2020-08-31 | 2020-09-04 | 0% |  |  | ¦
1.3.5 | New Product 1 แบบประกัน (Ocean Smart) (Cont.) | 2020-08-31 | 2020-09-04 | 0% |  |  | ¦
1.3.5.1 | E75 สมาร์ท โพรเทคชัน 99/99 (Agent) - (Cont.) | 2020-08-31 | 2020-09-04 | 0% |  |  | ¦
1.4 | SIT - Phase 0.2 (New Product, Flow Login, Health Check up-AMLO) | 2020-09-07 | 2020-09-11 | 0% |  |  | ¦
1.4.1 | New Product 3 แบบประกัน | 2020-09-07 | 2020-09-09 | 0% |  |  | ¦
1.4.1.1 | E73 สมาร์ท โกล 15/7 | 2020-09-07 | 2020-09-09 | 0% |  |  | ¦
1.4.1.2 | E74 สมาร์ท โกล 25/5 | 2020-09-07 | 2020-09-09 | 0% |  |  | ¦
1.4.1.3 | E75 สมาร์ท โพรเทคชัน 99/99 (Agent) | 2020-09-07 | 2020-09-09 | 0% |  |  | ¦
1.4.2 | Health Checkup-AMLO | 2020-09-07 | 2020-09-09 | 0% |  |  | ¦
1.4.2.1 | UI Validation Health | 2020-09-07 | 2020-09-09 | 0% |  |  | ¦
1.4.3 | ปรับ UX/UI, Flow การ Login, Lib | 2020-09-09 | 2020-09-11 | 0% |  |  | ¦
1.4.3.1 | Layout และการแสดงผล | 2020-09-09 | 2020-09-11 | 0% |  |  | ¦
1.4.3.2 | Flow การ Login | 2020-09-09 | 2020-09-11 | 0% |  |  | ¦
1.4.3.3 | รองรับ MSA Production | 2020-09-09 | 2020-09-11 | 0% |  |  | ¦
1.4.3.4 | Flag สำหรับ Version e-App | 2020-09-09 | 2020-09-11 | 0% |  |  | ¦
1.5 | UAT Round 1 - FNA/Mini-FNA,New Product | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.1 | การยกเลิกขายแบบประกัน FNA/Mini-FNA | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2 | New Product 10 แบบประกัน | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.1 | O188 (ปรับค่าคอม,ทุนต่ำ) | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.2 | O193 (ปรับค่าคอม,ทุนต่ำ) | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.3 | O539 เพื่อนคู่ชีวิต B450 (20/15) (ปรับค่าคอม) | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.4 | O218 สบายชัวร์ (ปรับค่าคอม) | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.5 | O496 ไทยสมุทรสบายสบาย 30/15 (ปรับค่าคอม) | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.6 | I154 คุ้มทวี (20/15) (ปรับค่าคอม) | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.7 | I156 คุ้มทวี 20/10 (ปรับค่าคอม) | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.8 | E73 สมาร์ท โกล 15/7 | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.9 | E74 สมาร์ท โกล 25/5 | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.2.10 | E75 สมาร์ท โพรเทคชัน 99/99 (Agent) | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.3 | Health Checkup-AMLO | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.3.1 | UI Validation Health | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.4 | ปรับ UX/UI, Flow การ Login, Lib | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.4.1 | Layout และการแสดงผล | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.4.2 | Flow การ Login | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.4.3 | รองรับ MSA Production | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.5.4.4 | Flag สำหรับ Version e-App | 2020-09-14 | 2020-09-18 | 0% |  |  | ¦
1.6 | Fixed Issue | 2020-09-21 | 2020-09-23 | 0% |  |  | ¦
1.6.1 | Fixed Issue UAT Rount 1 | 2020-09-21 | 2020-09-23 | 0% |  |  | ¦
1.7 | UAT Round 2 - Retest issue | 2020-09-23 | 2020-09-30 | 0% |  |  | ¦
1.7.1 | UAT Round 2 | 2020-09-23 | 2020-09-30 | 0% |  |  | ¦
2 | Phase 2 | 2020-09-14 | 2021-01-01 | 0% |  |  | ¦
2.1 | Sprint 20.19 | 2020-09-14 | 2020-09-25 | 0% |  |  | ¦
2.1.1 | Master & Mapping | 2020-09-14 | 2020-09-25 | 0% | Developer 1 |  | ¦
2.1.1.1 | Mapping User ตามช่องทาง | 2020-09-14 | 2020-09-25 | 0% |  |  | ¦
2.2 | Sprint 20.20 | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.1 | Master & Mapping (Cont.) | 2020-09-28 | 2020-10-09 | 0% | Developer 1 |  | ¦
2.2.1.1 | [None Agent] service login | 2020-09-28 | 2020-10-09 | 0% | รองรับ none agent, ปรับ UL เป็น Optional |  | ¦
2.2.1.2 | [None Agent] Mapping Product on NYX | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.2 | Sales illustration | 2020-09-28 | 2020-10-09 | 0% | Developer 2 |  | ¦
2.2.2.1 | การแสดงผลและการขายแบบประกันตามช่องทาง | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.2.1.1 | หน้าเสนอขาย - แบบประกันหลัก | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.2.1.2 | หน้าเสนอขาย - สัญญาเพิ่มเติม | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.2.1.3 | หน้าเสนอขาย - PA | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.2.1.4 | หน้าเสนอขาย - การแสดงผลเบี้ยประกัน และการลดหย่อนภาษี | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.2.1.5 | หน้าหลักเกณฑ์การทำประกัน | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.2.1.6 | หน้าแบบประกัน | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.3 | Sprint Review | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.2.3.1 | การ Mapping data - User, Product, Service Login | 2020-09-28 | 2020-10-09 | 0% |  |  | ¦
2.3 | Sprint 20.21 | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.1 | Master & Mapping (Cont.) | 2020-10-12 | 2020-10-23 | 0% | Developer 1 |  | ¦
2.3.1.1 | [None Agent] Setup Product on NYX | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.2 | NYX System | 2020-10-12 | 2020-10-23 | 0% | Developer 1 |  | ¦
2.3.2.1 | สร้างเอกสารเสนอขาย | 2020-10-12 | 2020-10-23 | 0% | ไปกลับระหว่าง Sals illus กับ NYX |  | ¦
2.3.2.2 | Webservice Mapping Product by Channel , Main plan+Rider | 2020-10-12 | 2020-10-23 | 0% | webservice Mapping Product by Channel, Mainplan+Rider |  | ¦
2.3.3 | Sales illustration (Cont.) | 2020-10-12 | 2020-10-23 | 0% | Developer 2 |  | ¦
2.3.3.1 | การแสดงผลและการขายแบบประกันตามช่องทาง | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.3.1.1 | หน้ามูลค่ากรมธรรม์ | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.3.1.2 | หน้าเปรียบเทียบแผนประกัน | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.3.1.3 | การแสดงผล PDF เอกสารเสนอขาย | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.4 | FNA System | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.4.1 | การเชื่อมต่อระหว่าง FNA กับ EROS | 2020-10-12 | 2020-10-23 | 0% | การเชื่อมต่อ Game เพื่อเลือกซื้อแบบประกัน |  | ¦
2.3.5 | Sprint Review | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.5.1 | Sales illustration - Functional ต่าง ๆ | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.5.2 | NYX - เอกสารเสนอขาย, Product by Channel , Main plan+Rider | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.3.5.3 | การเชื่อมต่อระหว่าง FNA กับ EROS | 2020-10-12 | 2020-10-23 | 0% |  |  | ¦
2.4 | Sprint 20.22 | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.4.1 | Ocean Smart | 2020-10-26 | 2020-11-06 | 0% | Developer 1 |  | ¦
2.4.1.1 | ปรับการ Login | 2020-10-26 | 2020-11-06 | 0% | รองรับ none agent, ปรับ UL เป็น Optional |  | ¦
2.4.1.2 | เชื่อมต่อระหว่าง FNA กับ EROS | 2020-10-26 | 2020-11-06 | 0% | (oceansmart://xxxx/yyyy) |  | ¦
2.4.2 | ปิดแบบประกัน | 2020-10-26 | 2020-11-06 | 0% | Developer 1 |  | ¦
2.4.2.1 | Product smart chanel | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.4.3 | FNA System | 2020-10-26 | 2020-11-06 | 0% | Developer 2 |  | ¦
2.4.3.1 | ปิดระบบ Sales illustration | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.4.3.2 | การบันทึกข้อมูลเลขตัวแทน 7 หลัก | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.4.3.3 | การอ่านแบบประกันบน Firebase | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.4.4 | Sprint Review | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.4.4.1 | Ocean Smart | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.4.4.2 | ปิดแบบประกัน | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.4.4.3 | เชื่อมต่อระหว่าง FNA กับ EROS | 2020-10-26 | 2020-11-06 | 0% |  |  | ¦
2.5 | Sprint 20.23 | 2020-11-09 | 2020-11-20 | 0% |  |  | ¦
2.5.1 | FNA System (Cont.) | 2020-11-09 | 2020-11-20 | 0% | Developer 2 |  | ¦
2.5.1.1 | การอ่านแบบประกันบน Firebase (Cont.) | 2020-11-09 | 2020-11-20 | 0% |  |  | ¦
2.6 | Sprint 20.24 | 2020-11-23 | 2020-12-04 | 0% |  |  | ¦
2.6.1 | FNA System (Cont.) | 2020-11-23 | 2020-12-04 | 0% | Developer 2 |  | ¦
2.6.1.1 | การอ่านและบันทึกข้อมูลลูกค้า ที่ firebase ไปเป็น database (Eros) | 2020-11-23 | 2020-12-04 | 0% |  |  | ¦
2.7 | Sprint 20.25 | 2020-12-07 | 2020-12-18 | 0% |  |  | ¦
2.7.1 | FNA System (Cont.) | 2020-12-07 | 2020-12-18 | 0% | Developer 2 |  | ¦
2.7.1.1 | การอ่านและบันทึกข้อมูลลูกค้า ที่ firebase ไปเป็น database (Eros) | 2020-12-07 | 2020-12-18 | 0% |  |  | ¦
2.7.2 | Sprint Review | 2020-12-07 | 2020-12-18 | 0% |  |  | ¦
2.7.2.1 | Overall FNA | 2020-12-07 | 2020-12-18 | 0% |  |  | ¦
2.8 | Sprint 20.26 | 2020-12-21 | 2021-01-01 | 0% |  |  | ¦
2.8.1 | FNA System (Cont.) | 2020-12-21 | 2021-01-01 | 0% | Developer 2 |  | ¦
2.8.1.1 | Data migration | 2020-12-21 | 2021-01-01 | 0% |  |  | ¦