## Doc
SIT Test Document
Project Code | 20180011
Project Name | Agent Portal Ver2
Test Phase | UAT
High Level Scope
Signature
Project Role | Name | Department | Signature | Sign Date | Remark
PM |  | ฝ่ายวิจัยและพัฒนาเทคโนโลยีสารสนเทศ
SA Lead |  | ฝ่ายวิจัยและพัฒนาเทคโนโลยีสารสนเทศ
SA |  | ฝ่ายวิจัยและพัฒนาเทคโนโลยีสารสนเทศ
QA Lead |  | ฝ่ายวิจัยและพัฒนาเทคโนโลยีสารสนเทศ
QA |  | ฝ่ายวิจัยและพัฒนาเทคโนโลยีสารสนเทศ
User |  | ฝ่ายการเงิน
User |  | ฝ่ายการเงิน
User |  | ฝ่ายการเงิน
User |  | ฝ่ายกิจการสาขา ด้านปฏิบัติการสาขา
User |  | ฝ่ายกิจการสาขา ด้านปฏิบัติการสาขา
User |  | ฝ่ายกิจการสาขา ด้านปฏิบัติการสาขา
User |  | ฝ่ายกิจการสาขา ด้านปฏิบัติการสาขา

## Test Summary
Test Summary Report
Project Code | 20180011
Project Name | Agent Portal Ver2
Project Manager | [PM]
Test Phase | UAT
Report Date | 2020-06-09
Plan Timeline | 2019-08- | - | 2019-08-23
Actual Timeline | 2019-08-13 | - | 2019-08-23
| Total Days | # of Days Spent | Remaining Days | Expected %Passed | % Ready for Test | Actual %Passed
| #REF! | #REF! | #VALUE! | 0% | 100% | 0%
|  |  |  | Ready for test |  |  | Total
|  |  |  | Not Start |  |  | 0
|  |  |  | In Progress |  |  | 0
|  |  |  | Pending |  |  | 0
|  |  |  | Failed |  |  | 0
|  |  |  | Passed |  |  | 0
|  |  |  | Cancelled |  |  | 0
Ready for Test | 100%
Not Ready for Test | 0%
Category | Test Status | % Test Progress (Test Status = In Progress, Failed, Passed, Cancelled) | % Passed (Test Status = Passed, Cancelled) | Responsible By | Start Date | Finish Date | Remark | Ready for test | [6 empty] | Not Ready for Test
[8 empty] | Not Start | In Progress | Pending | Failed | Passed | Cancelled | Total Test Cases
Service POST favorite | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service GET favorite | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service PUT favorite | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service POST favorite remark | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service GET favorite remark | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Not Start | 0% | 0% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Test Progress (Ready for Test) |  | 0% | 0% |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
% Test Progress (Overall) |  | 0% | 0% |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Jira Status | Priority |  |  |  |  | Total
| Blocker | Critical | Major | Minor | Trivial
Open | 0 | 0 | 0 | 0 | 0 | 0
In Progress | 0 | 0 | 0 | 0 | 0 | 0
Reopened | 0 | 0 | 0 | 0 | 0 | 0
Resolved | 0 | 0 | 0 | 0 | 0 | 0
Closed | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0
Major Issue/Concern
No. | Issue/Concern | Recommendation | Jira ID | Status | Responsible By | Target Completion Date | Remark
1
2
3

## Test Checklist
Test Checklist ID | Category | Sub Category | Test Objective | Test Condition | Test Step | Expected Result | Test Data | Priority | Test Status | Tested By | Tested Date | Jira No. | Remark
Service POST favorite
TC-postFavorite-001 | Service POST favorite |  | เพิ่มกลุ่ม favorite ใหม่ | ไม่มี กลุ่ม favorite ของ agent |  | สามารถบันทึกกลุ่ม favorite ตามตัวแทน ได้ถูกต้อง | { "agent_code":"1234567", "favorite_name":"สบายมาก" } | High
TC-postFavorite-002 | Service POST favorite |  | เมือ agent มีกลุ่ม ครบ 5 แล้วต้องบันทึกไม่ได้อีก | agent มีกลุ่มครบ 5 แล้ว |  | ไม่สามารถบันทึกกลุ่มเพิ่มได้อีกแล้ว | { "agent_code":"1234567", "favorite_name":"สบายมาก5" } | High
TC-postFavorite-003 | Service POST favorite |  | รหัส agent code ไม่ครบ 7 หลัก |  |  | ไม่สามารถบันทึกกลุ่มได้ | { "agent_code":"1267", "favorite_name":"สบายมาก5" }
TC-postFavorite-004 | Service POST favorite |  | รหัส agent code มากกว่า 7 หลัก |  |  | ไม่สามารถบันทึกกลุ่มได้ | { "agent_code":"1234567890", "favorite_name":"สบายมาก5" }
TC-postFavorite-005 | Service POST favorite |  | ชื่อกลุ่มมากกว่า 50 ตัวอักษร |  |  | ไม่สามารถบันทึกกลุ่มได้ | { "agent_code":"1234567", "favorite_name":"012345678901234567890123456789012345678901234567890123456789" }
Service GET favorite
TC-getFavorite-001 | Service GET favorite |  | ดึงข้อมูลกลุ่ม favorite | agent มี กลุ่มอยู่แล้ว 1 กลุ่ม |  | ดึงข้อมูลกลุ่ม ได้ 1 กลุ่ม | {"agent_code":"1234567"}
TC-getFavorite-002 | Service GET favorite |  | ดึงข้อมูลกลุ่ม favorite | agent ไม่มี กลุ่ม |  | ไม่แสดงชื่อกลุ่ม | {"agent_code":"1234537"}
TC-getFavorite-003 | Service GET favorite |  | ดึงข้อมูลกลุ่ม favorite | agent มี กลุ่มอยู่แล้ว 5 กลุ่ม |  | ดึงข้อมูลกลุ่ม ได้ 5 กลุ่ม | {"agent_code":"1234637"}
Service PUT favorite
TC-putFavorite-001 | Service PUT favorite |  | แก้ไข กลุ่ม favorite ได้ถูกต้อง | agent มีกลุ่ม favorite อยู่แล้ว |  | ทำการแก้ไขชื่อกลุ่มได้ถูกต้อง | { "favorited_id":12, "agent_code":"1234567", "favorite_name":"สบายมาก" }
TC-putFavorite-002 | Service PUT favorite |  | แก้ไข กลุ่ม favorite ข้าม ตัวแทน | agent แก้ไขกลุ่ม favorite ของ agent คนอื่น |  | ไม่สามารถทำการแก้ไขได้ | { "favorited_id":12, "agent_code":"1234569", "favorite_name":"สบายมาก" }
Note on N23: ใช้การเตือนและ focus ที่ช่องกรอกข้อมูลนั้นๆ แทนการแสดง Message ครับ -ekkavit duangchan - เอกวิทย์ ดวงจันทร์
Note on N24: ใช้การเตือนและ focus ที่ช่องกรอกข้อมูลนั้นๆ แทนการแสดง Message ครับ -ekkavit duangchan - เอกวิทย์ ดวงจันทร์

## Test Plan
Test Plan
Types of Testing
No. | Types of Testing | Test Scope | Responsible By | In Scopes of Testing? (Yes/No)
1 | Unit Test
1.1 | Unit Test (UT) | - Testing of individual components. - Testing of combined components as a stand alone module. | Developer
1.2 | Integration Test (IT) | - Involves building an application from its components and testing for problems that arise from component interactions. - Testing groups of components integrated to create sub-system or a system. - Testing of across modules end-to-end functions (without external interfaces). | Developer, System Analyst
2 | System Integration Test (SIT)
2.1 | Function Test (FT) | - Testing to ensure that software conforms with all the required functionality worked as expected requirements. | Tester
2.2 | System Integration Test (SIT) | - Whole product in integrated environment. - External Interfaces are connected and data can be processed. - Systems security testing. | Tester
3 | User Acceptance Test (UAT)
3.1 | User Acceptance Test (UAT) | - User security, roles & access rights. - Use case & product base testing. - End-to-end business testing. - All I/O reports (online & batch). | User
4 | Non Functional Test
4.1 | Performance Test | - User experience testing to validate SLA (batch and online based on expected usages). | Non Functional Tester
4.2 | Load Test | - User experience testing to validate load of the system as expected usage. | Non Functional Tester
4.3 | Penetration Test | - Security and ethical hacking. | Non Functional Tester, Vendor
Entry & Exit Criteria
System Integration Test (SIT)
No. | Entry Criteria
1 | Project plan, and resource allocation must be in placed, and agreed by stakeholders.
2 | Requirement document has been sign-off/acknowledge by users. - Business Requirement Document (BRD) - System Requirement Specification (SRS) - Change Request (if any)
3 | In-scope functionality completely delivered based on requirements.
4 | All developed code must be completely unit tested with completed Unit Test Report by development team.
5 | No outstanding blocker, critical, and major priority/severity defects. Less than 5 minor, and 5 trivial priority/severity defects.
6 | All client/server test hardware, tools, interface systems, test environments must be in placed.
7 | Environment configuration data has been defined and set up.
8 | SIT test preparation complete.
9 | Agreement with stakeholders on the following area:
Priority definition
Defect logging guideline
Service Level Agreement (SLA) to turnaround fixing of reported defects/bugs
Change management process
No. | Exit Criteria
1 | All planned test scope have been completed tested.
2 | No outstanding blocker, critical, and major priority/severity defects. Less than 5 minor, and 5 trivial priority/severity defects.
3 | In cases of outstanding defects remain, known issues must be acknowledged and approved by project team. (PM, QA Lead, User)
4 | SIT test document has been sign-off by PM.
User Acceptance Test (UAT)
No. | Entry Criteria
1 | Project plan, and resource allocation must be in placed, and agreed by stakeholders.
2 | Requirement document has been sign-off/acknowledge by users. - Business Requirement Document (BRD) - System Requirement Specification (SRS) - Change Request (if any)
3 | In-scope of UAT testing has been agreed with users.
4 | In-scope functionality completely delivered based on requirements.
5 | No outstanding blocker, critical, and major priority/severity defects. Less than 5 minor, and 5 trivial priority/severity defects.
6 | All client/server test hardware, tools, interface systems, test environments must be in placed.
7 | Environment configuration data has been defined and set up.
8 | UAT test preparation complete.
9 | Agreement with stakeholders on the following area:
Priority definition
Defect logging guideline
Service Level Agreement (SLA) to turnaround fixing of reported defects/bugs
Change management process
9 | SIT test document has been sign-off by PM.
No. | Exit Criteria
1 | All planned test scope have been completed tested.
2 | No outstanding blocker, critical, and major priority/severity defects. Less than 3 minor, and 3 trivial priority/severity defects.
3 | In cases of outstanding defects remain, known issues must be acknowledge and approve by project team. (PM, QA Lead, User)
Assumption
No. | Assumption
1 | เพื่อลดปริมาณการสำรองเงินในบัญชีเงินฝากธนาคารของบริษัท
2 | เพื่อพัฒนากระบวนการบริหารเงินระหว่างสำนักงานใหญ่และสาขา
3 | บริษัทสามารถรับทราบข้อมูลการทำธุรกรรมได้เร็วขึ้น
In Scopes of Testing
No. | In Scopes of Testing
1
2
3
4
5
Out Scopes of Testing
No. | Out Scopes of Testing
1
2
Impact/Related System
No. | System | Impacted/Related System
1
Test Deliverable
No. | Test Deliverable | Description
1 | Test plan | Describe test plan, type of testing, test activities, etc.
2 | Test cases and test results | Describe test objective, test condition determine whether system works as expected.
3 | Defect/incident log | Results of unexpected results.
4 | Test report | Summarize results of testing.
Test Device
No. | Browser/Version | OS | Remark
1 | Google Chrome (Latest version as of Test Execution Date) | Windows 7 Service Pack 1
2 | Google Chrome | iOS (Tablet/Mobile)
3 | Google Chrome | Android (Tablet/Mobile)
Test Tool
No. | Test Tool | Description
1 | Jira | Defect management system tool
2 | Libre office/Microsoft Office/Google sheet | Test case management tool
3 | Google Chrome | Web browser
4 | PicPick, Shutter | Screen capture tool
5 | SQuirreL SQL Client, DBeaver | Open-source Java SQL client program for any JDBC compliant database
6 | Oracle SQL Developer Tool | SQL developer tool
7 | Notepad ++, Scite Text Editor | Text editor tool (optional)
8 | Winmerge | Differencing and merging tool presenting differences in visual text format (optional)
9 | Wizdler | Parser WSDL files and generates SOAP message response (optional)
10 | Pentaho Data Integration Tool | ETL tool
11 | www.responsinator.com | Simulate responsive web site
12 | Draw.io | Flowchart maker
13 | JMeter | Open source software for load and performance testing
14 | NMAP | Security scanner used to discover hosts and services on a computer network
15 | Postman Interceptor | Chrome extension that functions as a proxy to capture HTTP or HTTPS requests
16 | https://securityheaders.io | Web security scanner (เลือกแบบไม่ Public ไปยัง Website ภายนอก)
17 | Burp Suite | Integrated platform for performing security testing of web applications
18 | Wireshark | Network protocal analyze tool
19 | NeoLoad | Software test and monitoring tools to improve the quality and performance of information systems
20 | Robotframework | Test automation framework
21 | ChroPath Chrome Extension | XPath finder with chrome extension
22 | Ranorex | Test automation framework
23 | Intruder Attack
Reference
No. | Reference | Remark
1
2
3
4

## Jira
Jira
Issue Type | Key | Summary | Priority | Status | Resolution | Assignee | Reporter | Created | Updated
Bug
Improvement

## Var
Phase | Test Status | Test Status Description | Yes/No | Issue Status | Priority | Category
Development | Not Ready for Test | Not Ready for Test = ส่วนที่ไม่พร้อมทดสอบ | Yes | Not Start | High | Service POST favorite
SIT | Not Start | Not Start = ยังไม่เริ่มทดสอบ | No | In Progress | Medium | Service GET favorite
Go-live | Pending | Pending = ไม่สามารถทดสอบต่อได้ |  | Completed | Low | Service PUT favorite
| Failed | Failed = ผลการทดสอบไม่ผ่าน |  |  |  | Service POST favorite remark
Service GET favorite remark
Service PUT favorite remark
| Passed | Passed = ผลการทดสอบผ่าน
| Cancelled | Cancelled = ยกเลิกการทดสอบ